## Sheet1
NHGRI SEQUENCING UPDATE as of 2/9/07
ORGANISM | SEQUENCING CENTER(S) | Q20 BASES IN TRACE REPOSITORY | OTHER INFORMATION
MOUSE, Mus musculus | BI/MIT, WUGSC, Sanger, BCM | 92101648420 | The genome was finished in December 2005. The MGSC met on February 9, 2007 to discuss analysis and publication of the mouse genome.
1,191,397 kb draft 3,707,802 kb finished
RAT, Rattus norvegicus | BCM | 26127838457 | The Rat Genome Sequencing Project Consortium published the genome sequence and comparative analysis of the Brown Norway rat in the April 1, 2004 issue of Nature.
5,036,842 kb draft 68,479 kb finished
ALPACA, Vicugna vicugna | WUGSC | 11102456 | Sequencing ongoing.
AMOEBA, Acanthamoeba castellanii | BCM | 57317490 | Sequencing ongoing.
ARMADILLO, Dasypus novemcinctus | BI/MIT | 7577917469 | Sequencing (2X) complete and assembly released.
BOVINE, Bos taurus | BCM | 26815778117 | The Bovine Genome Sequencing Project Advisory Committee meets monthly by telephone to discuss project progress and strategy. A new assembly was released in September 2006.
BUSHBABY, Otolemur garnetti | BI/MIT | 5859592420 | Sequencing (2X) complete and assembly released.
CAENORHABDITIS BRIGGSAE | WUGSC | 1070775063 | Sequencing complete and assembly released.
CAENORHABDITIS JAPONICA | WUGSC | 524164436 | Sequencing ongoing.
CAENORHABDITIS N. SP. CB5161 | WUGSC |  | Sequencing complete and assembly ongoing.
CAENORHABDITIS REMANEI | WUGSC | 1457554791 | Sequencing complete and assembly ongoing.
CHICKEN, Gallus gallus | WUGSC | 9156576090 | The first assembly of the chicken genome was released on March 1, 2004 and published in Nature on December 9, 2004.
CHIMPANZEE, Pan troglodytes | WUGSC, BI/MIT | 26180841240 | Chimp draft assembly completed and paper published on September 1, 2005 in Nature. The WUGSC is also producing deeper sequencing coverage of the chimpanzee genome.
DOG, Canis familiaris | BI/MIT | 22269507740 | Dog draft assembly completed and paper published in Nature on December 8, 2005 (7.6X coverage).
DOLPHIN, Turisops truncatus | BCM | 6144122621 | Sequencing (2X coverage) complete and in assembly.
DOMESTIC CAT, Felis catus | Agencourt | 5411746173 | Sequencing complete (2X) and assembled (Aug '05).
DROSOPHILA ANANASSAE | Agencourt | 2036784674 | Sequencing (8X) complete and assembled.
DROSOPHILA GRIMSHAWI | Agencourt | 1544244407 | Sequencing (8X) complete and assembled (September 2006).
DROSOPHILA MOJAVENSIS | Agencourt | 1543839342 | Sequencing (8X) complete and assembled.
DROSOPHILA PERSIMILIS | BI/MIT | 845994748 | Sequencing (4X) complete and assembled.
DROSOPHILA PSEUDOOBSCURA | BCM | 1688488875 | First freeze assembly of D. pseudoobscura was released in August 2003.
DROSOPHILA SECHELLIA | BI/MIT | 755647847 | Sequencing (3X) complete and assembled.
DROSOPHILA SIMULANS | WUGSC | 1707496092 | Sequencing (3X) of w501 strain and 1-fold coverage of 6 other strains complete. 3 assemblies currently available (including deeper coverage of w501 strain).
DROSOPHILA VIRILIS | Agencourt | 1950167022 | Sequencing (9X) complete and assembly released in July 2004.
DROSOPHILA YAKUBA | WUGSC | 1597515109 | Sequencing (6X) complete and assembly released in April 2004 (additional coverage-automated sequence improvement expected Fall '05).
DUCK-BILLED PLATYPUS, Ornithorhynchus anatinus | WUGSC | 18447395203 | Sequencing complete and assembly ongoing.
ELEPHANT, AFRICAN SAVANNAH, Loxodonta africana africana | BI/MIT | 7060707396 | Sequencing (2X coverage) and assembled.
EUROPEAN COMMON SHREW, Sorex araneus | BI/MIT | 6124319274 | Sequencing (2X coverage) and assembled (Oct '05).
FROG, Xenopus tropicalis | JGI, WUGSC | 13370087872 | Sequencing (8X) complete and assembly ongoing.
GUINEA PIG, Cavia porcellus | BI/MIT | 7585934889 | Sequencing (2X coverage) and assembled.
GREEN ANOLE LIZARD, Anolis carolinensis | BI/MIT | 11704603748 | Sequencing complete and in assembly.
GROUND SQUIRREL, Spermophilis tridecemlineatus | BI/MIT | 4977187107 | Sequencing (2X coverage) and assembled.
HEDGEHOG, Erinaceus europeaus | BI/MIT | 6627313001 | Sequencing (2X) complete and assembly released.
HONEYBEE, Apis mellifera | BCM | 2503660866 | Assembly version 1.1 was released in January 2004.
HYDRA, Hydra magnipapillata | JCVI | 7985976353 | Sequencing complete and assembly ongoing.
HYRAX, Procavia capensis | BI/MIT | 6879696487 | Sequencing complete and assembly ongoing.
LITTLE BROWN BAT, Myotis lucifigus | BI/MIT | 5142050847 | Sequencing (2X coverage) and assembled.
MARMOSET, Callithrax Jacchus | BCM, WUGSC | 19804747144 | Sequencing ongoing.
MOSQUITO, Anopheles gambiae | WUGSC, JCVI | 6215578362 | Sequencing complete and assembly ongoing.
MOUSE LEMUR, Microcebus murinus | BI/MIT | 2649524019 | Sequencing ongoing.
NEMATODE, Pristionchus pacificus | WUGSC | 1454920685 | Sequencing ongoing.
OPOSSUM, LABORATORY, Monodelphis domestica | BI/MIT | 25091568071 | Sequencing complete and assembly released (Jan '06).
ORANGUTAN, Pongo pygmaeus | WUGSC, BCM | 10204866061 | Sequencing complete and assembly ongoing.
PEA APHID, Acyrthosiphon pisum | BCM | 929159614 | Sequencing complete and assembly ongoing.
PLANARIAN, Schmidtea mediterranea | WUGSC | 9942413392 | A draft assembly (5X) has been completed.
RHESUS MACAQUE, Macaca mulatta | Agencourt, BCM, JCVI, WUGSC | 19672545077 | Sequencing complete and assembly released.
RED FLOUR BEETLE, Tribolium castaneum | BCM | 1589094481 | Sequencing (7X) complete and assembly ongoing.
RABBIT, Oryctoloagus cuniculis | BI/MIT | 6387505440 | Sequencing (2X) complete and assembly released.
SEA URCHIN, Strongylocentrotus purpuratus | BCM | 8553875768 | Sequencing and assembly complete.
SEA LAMPREY, Petromyzon marinus | WUGSC | 9577492750 | Sequencing ongoing.
SEA SLUG, Aplysia californica | BI/MIT | 2491640624 | Sequencing ongoing.
SNAIL, Biomphalaria glabrata | WUGSC | 21874423 | Sequencing ongoing.
SPIROTRICH CILIATE PROTOZOAN, Oxytricha trifallax | BI/MIT, WUGSC | 493944811 | Sequencing ongoing.
STICKLEBACK, Gasterosteus aculeatus | BI/MIT | 4272094468 | Sequencing complete and assembly released (Jan '06).
TARSIER, Tarsius syrichta | WUGSC | 3705836360 | Sequencing ongoing.
TENREC, Echinops telfairi | BI/MIT | 6626482279 | Sequencing (2X) complete and assembly released.
TREE SHREW, Tupaia belangeri | BI/MIT | 5666226090 | Sequencing (2X) complete and assembly released.
WALLABY, Macropus eugenii | BCM | 4578291734 | Sequencing complete and assembly ongoing.
WASP, Nasonia giraulti | BCM | 427760069 | Sequencing complete and assembly ongoing.
WASP, Nasonia longicornis | BCM | 7919849 | Sequencing complete and assembly ongoing.
WASP, Nasonia vitripenis | BCM | 3190740406 | Sequencing complete and assembly ongoing.
ZEBRA FINCH, Taeniopygia guttata | WUGSC | 6871281001 | Sequencing ongoing.
FUNGAL GENOME INITIATIVE | BI/MIT
Aspergillus nidulans |  |  | 13X Genome Assembly released Feb 2003.
Candida albicans (Strain WO-1) |  | 151160938
Candida guilliermondii |  |  | 10X Genome Assembly released September 2004.
Candida lusitaniae |  |  | 9X Genome Assembly released September 2004.
Candida tropicalis |  | 136577434 | 10X Genome Assembly released January 2005.
Chaetomium globosum |  | 278613383 | 7X Genome Assembly released December 2004.
Coccidioides immitis |  | 439771572 | 10X Genome Assembly released March 2004.
Coprinus cinereus |  | 390734685 | 10X Genome Assembly released July 2003.
Cryptococcus neoformans Serotype A |  | 342137736 | 11X Genome Assembly released May 2003.
Cryptococcus neoformans Serotype B |  |  | 6X Genome Assembly released August 2004.
Histoplasma capsulatum |  | 173332616
Lodderomyces elongisporus |  | 192443302
Podospora anserina |  | 83777350
Rhizopus oryzae |  | 450768570 | 10X Genome Assembly released November 2004.
Saccharomyces cerevisiae RM11-1a |  |  | 10X Genome Assembly released September 2004.
Uncinocarpus reesei |  | 138704174
Ustilago maydis |  | 179849795 | 10X Genome Assembly released May 2003.